## Slide 1: Client Services Priorities
Complete Processes, Forms, Policies
Onboard Managed Lives
Support Managed Lives – Monitoring & Alert Management
New Initiatives / Projects

## Slide 2: Weekly Status Update Format
Key Client Services Metrics follow-up from LT meeting
Health Facilitation team update: Outcomes, Significant open items
  Processes, Policies, Forms
  Improvement initiatives
Current customer status: Metrics, Onboarding, Monitoring, Projects / Initiatives
  CMMC
  ECN
  SDPC
  RHCI

## Slide 3: Processes, Forms, Policies
Processes
  Onboarding / Enrolling Patients - Done
  Medication Reconciliation – Open issue on signoff being discussed by Bill and Steve
  Monitoring - Done
  Alert Handling – Document reviewed; finalizing diagram
  Need to close with Dr. Goldstein, others? – Next steps?
Policies and Training
  HIPAA – In Progress
  Security – Not started
Contracts and Insurance – In Progress